## Backlog grooming
Pre-Check | ScrumMaster | □ Video conference, screen share and/or polycom access information set up and shared
□ Schedule meeting space
□ Prepare and publish agenda
□ Check calendars for company holidays, training, events, travel and employee time off
□ For tactile artifacts: Replenish supplies of markers, post-its, 3x5 cards, pens,pins, etc.
| Product Owner | □ Ensure backlog item candidates are ready,according to the team's definaition of ready(if a definition of ready exists for the team)
□ Make sure the skills and capabilities of team members are known and are generally aligned with the needs of the backlog item candidates for the sprint.
| Development Team | □ Update the team's definition of done,as needed,and make sure it is easy to reference during the meeting
Open | Product Owner | □ Present the prodcut backlog items the product owner wants to have estimated.
| Development Team | □ Play planning poker for hose vacklog items.
| Product Owner&Development Team&ScrumMaster | □ In case the Bancklog item is large but needs to go into the next or subsequent Sprints,the team will split the backlog item into smaller backlog item.Re-size the new Backlog item by playing planning Poker for it again.
□ Review how the story is worded
□ Make sure it makes sense and that it conveys what is really needed.
□ Acceptance criteria expresses how the team will understand if they have met the story’s business need. The acceptance criteria, not only provides a set of test cases, but also provides additional definition to the user story
□ Add User Stories (if needed): New stories can come from many angles. As stories are broken down new stories will be naturally created. The process of grooming generates a significant level of data sharing which will cause the participants to discover new stories. New stories need to be added to the backlog.
□ Re-size backlog items that are not done but likely to be a request for the next three Spints.
□ Identify Backing items that need to be clarified for the next Backlog Grooming Meeting
Backlog Grooming Goal | ScrumMaster | □ For strategic planning you need to know the size of the Backlog items.It is a necessary input for release planning andfor gaining an understanding of how much a team might be able to develop in a sprint
| Development Team | □ See what will happen in the following phases of the project.
| Product Owner&Development Team&ScrumMaster | □ Grooming Backlog items:get better understanding for backlog items by decomposing them if appropriate.
Output | Development Team&ScrumMaster | □ Estimated Product Backlog
□ Smaller backlog items
□ issues that need to be clarified
Close | Dev Team | □ Next steps: What will each team member start working on when they walk out of this meeting? Have each team member select one task to begin working on.
□ Update your task board or agile tool to reflect what everyone is starting to work on.
| ScrumMaster | □ If issues came up during the meeting that require follow up outside of the meeting(such as organizational impediments,items not related to the sprint, etc), make sure they are documented and assigned for follow up as needed.

## Sprint Planning Checklist
Pre-Check | ScrumMaster | □ Video conference, screen share and/or polycom access information set up and shared
□ Schedule meeting space
□ Prepare and publish agenda
□ Check calendars for company holidays, training, events, travel and employee time off
□ For tactile artifacts: Replenish supplies of markers, post-its, 3x5 cards, pens, pins
| Product Owner | □ Ensure backlog item candidates are ready,according to the team's definaition of ready(if a definition of ready exists for the team)
□ Make sure the skills and capabilities of team members are known and are generally aligned with the needs of the backlog item candidates for the sprint.
| Development Team | □ Update the team's definition of done,as needed,and make sure it is easy to reference during the meeting
Open | ScrumMaster,Product Owner & Dev Team | □ Introductions (for new teams)
□ Review of purpose and agenda (for new teams)
□ Review team’s ground rules, as needed
□ Are any scrum team members (ScrumMaster, Product Owner or Development Team) missing? Why?
Sprint Goal & User Stories | Product Owner | □ Review current situation (product vision, roadmap, release plan or story map, etc) as needed
□ Sprint Goal: What is it and how will we know when we’ve accomplished it?
| Dev Team | □ Sprint Capacity: Based on the team’s velocity and experience, how much can we take on this sprint? | □ Story Points: What is our established velocity? Use this as an input to determine how many story points should be accepted.The team should always be looking to stretch beyond what they’ve done in the past.
□ Hours: Has the team established what its effective day (actual working hours/day) is? If the team uses tasks to break down user stories, how many hours are available this sprint?
□ Are all maintenance and overhead candidates estimated with story points so that they can be planned within capacity appropriately?
□ Are there any special circumstances this sprint that we need to take into consideration, like holidays, time off, trainings, company events, big demo, etc.?
| Product Owner & Dev Team | □ Review candidate backlog items for the sprint | □ Does each candidate user story support the sprint goal?
□ Is everyone clear about the desired outcome?
□ Is the sum of all story points accepted for the sprint greater than the amount agreed upon by the team? If so, the Product Owner needs to decide which of the lower priority items to take out.
□ Most teams will do 6-10 user stories per sprint.
□ User stories should be 8 points or less to be accepted into a sprint.
Sprint Backlog | Product Owner & Dev Team | □ What is the next highest priority item to deliver this sprint? Plan that one next.
□ What else do we need to understand about this story?Is the deliverable clear?Do the acceptance criteria adequately define the requirements of the story,and are they clear?
| Dev Team | □ Do we understand our implementation approach for this story?Do we need to have a quick whiteboard design discussion now,or perhaps schedule one as part of the story work?
□ What is our tactical approach for delivering this story? Can we list out the things we need to do? The things we need to do (tasks) can be captured on our task board or in our agile tool.
□ What is our estimated effort for the work needed to deliver this story? Work (tasks) can estimated in the number of work hours it would take to complete each task. Ideally, tasks should be able to be accomplished in a day.
□ Are we considering all the work that is needed to fully complete and deliver the story(get it to"Done")?We should check to make sure we are including everything from our team's Definition of Done
□ Is this user story,and its tasks,conducive to swarming so that one team member can take on one task at a time?
| Dev Team & Product Owner | □ Having now planned the work to be done,is it still sized appropriately?
Sprint Backlog Verification | Dev Team | □ Check for conflicts:Can the set of stories in our sprint vacklog be accomplished together in this sprint?Consider if there will be conflicts and how to resolve them.Adjust as needed.
□ Definition of Done:Will we be able to deliver a fully"Done"increment of our product at the end of this sprint?We should check to make sure we are including everything from our team's definition of done.
| Dev Team & Product Owner | □ Missing Backlog Items: Is the team aware of any work that needs to be done that is not included in the sprint backlog, including maintenance and overhead items, spikes, release planning activities, or any other activity that needs to be accomplished this sprint? If so, add them to the backlog, estimate them, re-calculate total points, and adjust sprint backlog as needed to fall within the number of points agreed by the team.
| Dev Team | □ Risks: Are there any other risks or circumstances that we need to be aware of during this sprint? If so, have we included resolving these things in our sprint plan?
□ Commitment:As a team ,can we commit to our spint plan?Can we describe how we intend to deliver the spint?"Commitment"means we agree our plan seems achievable, and we agree to work to our plan.
| Dev Team & ScrumMaster | □ Task board & burndown setup: Has our sprint plan been completely captured on our task board or in our agile tool? Are we ready to begin tracking our sprint, including producing sprint burndowns or other metrics we use?
Close | Dev Team | □ Next steps: What will each team member start working on when they walk out of this meeting? Have each team member select one task to begin working on.
□ Update your task board or agile tool to reflect what everyone is starting to work on.
| ScrumMaster | □ If issues came up during the meeting that require follow up outside of the meeting(such as organizational impediments,items not related to the sprint, etc), make sure they are documented and assigned for follow up as needed.

## Sprint Review Checklist
Pre-check | Scrum Master | □ Schedule meeting space
□ Prepare and publish agenda
□ Invite every one of our company, including CEO, product manager and so no, even the end users.
□Do every one of us know the object of this sprint?
□Is the Backlog of this product accessible and visible for everyone?
□Is the team has prepared workstations, device etc. to demonstrate the new functionality?
□Task board, sticky notes, markers
General | Product Owner | □Remind the purpose of this Sprint: Sprint goal, Stories the Scrum-Team had selected for this Sprint
| Scrum Master | □Show what the team has built during the last Sprint
□Tell the story of the sprint: How did it go? Did you have level 3 support incidents? Was anyone sick? New team members? Anything else important?
□Give a status of the sprint and an overview of which stories were finished and which ones weren't
| Product Owner | □Remind the plan of this Sprint and give people context about where we're at in the greater scale of things
Presentation | Team | □The team presents the Sprint results and demonstrates the new functionality, Backlog Item after Backlog Item
□The team shows the defects or difficulty points of this Sprint
| Product Owner | □Checking whether the Item is completed. □Coding □Testing □Documentations □Code review
| Users | □End user play with the new functionality
Review | All | □Everyone could voice his opinions and take questions
| Product Owner | □If the Product Owner wants to change a feature, add a new Backlog Item to the Product Backlog
□If a new idea for a feature occurs,add a new Backlog Item to the Product Backlog
| All | □If there is a feature that someones think it's useless, vote for it
| Product Owner & team | □If the team reports an impediment which is not solved yet, add the impediment to the Impediment Backlog
Conclusion | Scrum Master | □Collect feedback
□Summary the result of this Sprint.
□Summary the status of present product
□Summary the status of each Backlog Item
| Scrum Master & Product Owner | □Evaluate the quality and efficiency of each team
□Arrange the work next step
Close | Scrum Master | □Ensure the Product Backlog has been updated
□Ensure the Impediment Backlog has been updated
□Ensure the meeting record has been finished

## Scrum Retrospective Checklist
Pre-check | Scrum Master | □ Schedule meeting space
□ Prepare and publish agenda to all participants
□ Invite the participants: Scrum Master, all team members, (Optional) Product Owner
□ Do every participants know the object of this sprint?
□ Is the Backlog of this product accessible and visible for everyone?
□ Prepare the text markers for all participants, post-its, whiteboard and flip chart □A flip chart with the Prime Directive □A time-line over at least 3 connected flip charts □A flip chart with "What went well" □A flip chart with "What could be improved" □A flip chart with "Who is in Control" divided in 2 areas "team" and "organization"
General | Scrum Master | □ Introduce the goal of the meeting, review the agenda and format
□ Prior Retrospectives: Locate output from previous retrospectives for this project team - you'll be using this to check on the effectiveness of the chosen improvements and to remind everyone of previously discovered improvement needs.
□ Hand out a block of post-its to each participant
□ Explain how to work with the post-its
Ask & Opinions | Scrum Master | □ Ask everyone to write on them all significant events of this sprint; Timebox: 5 min
| Team | □ Each participant in turn adds his Post-its to the time-line and explains in two sentences the story behind each event
| Scrum Master | □ Ask everybody to write on them “What went well”; Timebox: 5 min.
| Team | □ Each participant in turn adds his Post-its to the flp chart “What went well” and explains it
| Scrum Master | □ Ask everybody to write on them “What could be improved”; Timebox: 5 min.
| Team | □ Each participant in turn adds his Post-its to the flp chart “What could be improved” and explains it
| Scrum Master | □ For each item on the “What could be improved” flp chart: □ ask the team “Who is in control of this impediment?” □ move the Post-it to the corresponding column on the flp chart “Who is in control”
Analyze | Scrum Master & Team | □ Discuss and come to a common understanding of the project's performance. Use the data that you have just created and reviewed. Say on this point until you've come to a consensus view
□ Analyze. Look for indicators of big issues, trends over time if you have historical data for your analysis, confusing or inconsistent information (e.g., product quality and delivery velocity is up but customer satisfaction is down) and significant highlights (e.g., product quality was greatly improved).
□ Comparison. Compare the past and present and get the success points or failure points of this Sprint
□ Prioritize both lists with the team
□ Decide the improvement action and discuss its expected benefits
| Scrum Master | □ Add the selected improvement action to the next iteration's sprint backlog.
□ Evaluate each group.Utilize a structured method of identifying the significance of the identified problems.
Conclusion | Scrum Master | □ Collect feedback on the retrospective. Offer each participant an opportunity to express their degree of satisfaction or perhaps a suggestion for the next retrospective
□ Summary "What went well"
□ Summary "What could be improved"
□ Summary "What to do now"
□ The impediments related to the organization are added to the Impediment Backlog
□ The impediments related to the team are added to the Product Backlog
Close | Scrum Master | □Ensure the Product Backlog has been updated
□Ensure the Impediment Backlog has been updated
□Ensure the meeting record has been finished
□ Publish the retrospective results to the team and others with an interest. □The data and analysis information that was created prior to and presented during the meeting □The data generated during the meeting (This and other information created during the meeting could be published either as pictures taken during the retrospective or as transcribed from notes taken during the meeting) □The grouping of insights □The selected improvement actions and expected benefits □Any updates made to the improvement action backlog.